## Milestones
AI Assistant core module
S. No | Module | Milestone | Task | Resource | Start Date | End Date
1 | NLP Module | Objective: To process and understand user queries, such as entity recognition and intent detection.
|  | Milestone 1 | Requirement Analysis and Design Objective: Clearly define the scope, functionalities, and performance requirements of the NLP module. Tasks: Identify the types of user queries the system will handle. Define the entities and intents that need to be recognized. | BA Team | 2024-06-19 | 2024-06-25
|  | Milestone 2 | Data Collection and Preparation Objective: Gather and prepare the data necessary for training and testing the NLP models. Tasks: Collect a diverse set of user queries relevant to the target domain. Annotate the data with entities and intents. | BA Team | 2024-06-19 | 2024-06-25
|  | Milestone 3 | Model Selection and Development Objective: Select and develop the models for entity recognition and intent detection. Tasks: Choose appropriate algorithms or frameworks (e.g., spaCy, BERT, Rasa, custom neural networks). Split the data into training, validation, and test sets. Perform data cleaning and preprocessing (e.g., tokenization, stemming, stop-word removal). Develop entity recognition models. Develop intent detection models. Train and fine-tune the models using the prepared dataset. | Esakki PethanRaj | 2024-06-19 | 2024-06-25
|  | Milestone 4 | Optimization and Performance Tuning Objective: Optimize the performance of the NLP module to ensure it meets response time and accuracy requirements. Tasks: Optimize model inference times. Tune hyperparameters for better performance. Implement caching mechanisms where appropriate. | Esakki PethanRaj | 2024-06-26 | 2024-02-07
2 | Query Processing & Prompt Generator | Objective: The query analyzer processes the user query and create prompts for the LLMs.
|  | Milestone 1 | Query Processing Development Objective: Develop and implement the query processing module to analyze user queries. Tasks: Integrate preprocessing steps (e.g., tokenization, normalization) into the query processing pipeline. Train and validate the models using the prepared dataset. Prompt Generator Development Objective: Develop the prompt generator module to create prompts for LLMs based on the analyzed queries. Tasks: Design prompt templates for various scenarios and contexts. Implement logic to select and populate prompt templates based on the query analysis results. Integrate the prompt generator with the query processing module. | Murali Swetha | 2024-06-19 | 2024-06-25
|  | Milestone 2 | Integration with LLMs Objective: Ensure seamless integration of the query processing and prompt generator modules with the LLM. Tasks: Implement APIs or interfaces to send processed queries and generated prompts to the LLM. Ensure the LLM can respond appropriately to generated prompts. Develop error handling and fallback mechanisms for unrecognized queries or failed prompts. | Murali Swetha | 2024-06-26 | 2024-02-07
3 | Image to Text | Objective: Applying Image processing techniques to medical prescription & notes to convert into text.
|  | Milestone 1 | Data Collection and Preparation Objective: Gather and prepare datasets of medical prescriptions and notes for training and testing. Tasks: Collect a diverse set of medical documents, including handwritten and printed examples. Annotate the documents with ground truth text for OCR training. | BA Team | 2024-06-19 | 2024-06-25
|  | Milestone 2 | Image Processing Development Objective: Develop and implement image processing techniques to enhance the quality of medical documents. Tasks: Implement techniques for noise reduction, contrast enhancement, and binarization. Develop methods for skew correction and alignment of text regions. Extract regions of interest (ROIs) where text is likely to be located. Test and validate the effectiveness of image processing techniques on the dataset. | Thangam Suresh | 2024-06-19 | 2024-06-25
|  | Milestone 3 | OCR Development Objective: Develop and integrate an OCR module to extract text from processed images. Tasks: Choose appropriate OCR frameworks or libraries (e.g., Tesseract, Google Cloud Vision, Amazon Textract). Train custom OCR models, especially for handwritten text recognition. Implement text extraction from identified ROIs. Validate the accuracy of the extracted text against the annotated dataset. | Thangam Suresh | 2024-06-26 | 2024-02-07
4 | Data Fetching (RAG) | Objective: To manage communication with external systems & Retrieve relevant data (e.g., internal system APIs, 3rd party systems, web search).
|  | Milestone 1 | RAG Model Integration Objective: Integrate the Retrieval-Augmented Generation (RAG) model into the API Gateway. Tasks: Choose an appropriate RAG framework or library (e.g., Hugging Face Transformers). Develop mechanisms to query the RAG model for relevant data retrieval. Integrate the RAG model with the API Gateway to handle data augmentation. Implement caching mechanisms to optimize repeated queries. | Kiriprabu NaveenRam | 2024-06-19 | 2024-06-25
|  | Milestone 2 | Objective: Develop the data fetching and aggregation logic. Tasks: Implement data fetching logic for internal system APIs. Implement data aggregation and normalization to combine data from multiple sources. | Kiriprabu NaveenRam | 2024-06-26 | 2024-02-07
5 | LLMs (e.g., GPT-4) | Objective: To generate responses based on the processed input (user query + generated prompt + relevant data).
|  | Milestone 1 | Integration with Data Fetching Objective: Integrate the LLM with the data fetching module to utilize relevant data in response generation. Tasks: Develop mechanisms to combine user queries, generated prompts, and retrieved data. LLM should access and utilize the relevant data fetched by the API Gateway. Implement logic to handle different data formats and integrate them into the response generation process. | Subash GomathiSankar | 2024-06-19 | 2024-06-25
|  | Milestone 2 | Context Management Objective: Develop methods to manage context and maintain coherence in multi-turn conversations. Tasks: Implement techniques to track and store conversation context (e.g., using short-term and long-term memory). Develop logic to retrieve and update context information as the conversation progresses. Ensure the LLM utilizes the context effectively to generate coherent responses. Validate the context management methods using real-world conversation scenarios. Validate the accuracy of the extracted text against the annotated dataset. | Subash GomathiSankar | 2024-06-26 | 2024-02-07
6 | Storage | Objective: Short Term (Redis DB) & Long Term Memory (Document based DB, NoSQL DB) for context and token storage.
|  | Milestone 1 | Redis Integration for Short-Term Memory Objective: Integrate Redis for short-term context and token storage. Tasks: Design the schema for short-term context storage in Redis. Implement functions to store and retrieve data in Redis. Develop mechanisms to handle data expiration and eviction policies in Redis. Test the Redis integration with simulated conversation data to ensure reliability. NoSQL Database Integration for Long-Term Memory Objective: Integrate a document-based NoSQL database (e.g., MongoDB) for long-term context and token storage. Tasks: Design the schema for long-term storage in the NoSQL database. Implement functions to store and retrieve data in the NoSQL database. Develop mechanisms to handle data versioning and historical context storage. Test the NoSQL database integration with real-world data scenarios to ensure reliability. | Naresh Dinesh | 2024-06-19 | 2024-06-25
|  | Milestone 2 | Context Management Logic Objective: Develop the logic to manage and transition between short-term and long-term memory. Tasks: Implement logic to save conversation context to Redis during active sessions. Develop functions to move data from Redis to the NoSQL database for long-term storage. Implement retrieval functions to fetch historical context from the NoSQL database. | Naresh Dinesh | 2024-06-26 | 2024-02-07
Milestone 5: Context Management Logic
Objective: Develop the logic to manage and transition between short-term and long-term memory.
Tasks:
Implement logic to save conversation context to Redis during active sessions.
Develop functions to move data from Redis to the NoSQL database for long-term storage.
Implement retrieval functions to fetch historical context from the NoSQL database.

## Modules
AI Assistant core module
S. No | Module | Task | Resource | Start Date | End Date
1 | NLP Module | To process and understand user queries, such as entity recognition and intent detection. | Esakki PethanRaj | 2024-06-19 | 2024-02-07
2 | Query Processing & Prompt Generator | The query analyzer processes the user query and create prompts for the LLMs. | Murali Swetha | 2024-06-19 | 2024-02-07
3 | Image to Text | Applying Image processing techniques to medical prescription & notes to convert into text. | Thangam Suresh | 2024-06-19 | 2024-02-07
4 | API Gateway - Data Fetching (RAG) | To manage communication with external systems & Retrieve relevant data (e.g., internal system APIs, 3rd party systems, web search). | Kiriprabu NaveenRam | 2024-06-19 | 2024-02-07
5 | LLMs (e.g., GPT-4) | To generate responses based on the processed input (user query + generated prompt + relevant data). | Subash GomathiSankar | 2024-06-19 | 2024-02-07
6 | Storage | Short Term (Redis DB) & Long Term Memory (Document based DB, NoSQL DB) for context and token storage. | Naresh Dinesh | 2024-06-19 | 2024-02-07